## Slide 1
APP AS CODE
CI/CD Platform | Project Summary
Programme Project Review
June 2026 | Platform Engineering
📌 SCOPE
Phase 1 – App as Code CI/CD Platform (FROZEN BASELINE v1.0)
In Scope
• GitHub Actions CI/CD: build → scan → test → release → promote
• Golden AMI build (Ansible) + IaC provisioning (Terraform)
• Security gates: SAST, secret scan, image scan (ECR/Inspector)
• Environments: dev → test → prod with approval gates
• Drift detection, auto-remediation & compliance evidence (S3)
• Runtimes: WebLogic→Tomcat migration, Apache Tomcat, Python
Out of Scope (Phase 1)
• ServiceNow integration (Phase 2)
• Digital signature controls | App source-code logic/testing
📅 PROJECT PLAN
Milestone
✅ Architecture Baseline frozen (v1.0 – Jun 2026)
✅ Component context + C4 diagrams complete
✅ Requirement Traceability Matrix (001–008) met
✅ Pipeline scaffold + Terraform / Ansible ready
🔄 POC – Tomcat ECS/Fargate (in progress)
⬜ ServiceNow integration (Phase 2)
⬜ Newcastle Workshop – Show & Tell
Promotion Model
dev (auto) → test (quality gate) → prod (manual approval)
Fail-closed: rejected release IDs blocked via SSM Decision Records
⚠️ RISKS & ISSUES
Risks
🔴 WebLogic apps: Fargate multicast not supported → must migrate to Tomcat first
🔴 OAM/Ping IdP apps: must switch to Entra ID before containerisation
🟡 Windows containers: large image size, limited Fargate support
🟡 COTS products: vendor support & licensing assessment required
🟡 Stateful apps: session externalisation to Redis required
Issues
⚠️ Terraform ECS/Fargate Tomcat resources not yet provisioned (POC gap)
⚠️ Deploy-dev job still placeholder – real ECS deployment pending
⚠️ FR-04 evidence schema/reporting deferred to Phase 2
🔗 DEPENDENCIES
AWS Platform
• AWS OIDC trust configured per env (dev / test / prod accounts)
• IAM roles: AWS_DEV / TEST / PROD_ROLE_ARN provided
• VPC / subnets / SGs pre-provisioned before POC execution
Identity & Access
• Microsoft Entra ID app registration (Identity team)
• All non-Entra IdPs (OAM, Ping) must migrate before onboarding
GitHub
• GitHub Environments (dev/test/prod) with required reviewers
• GitHub Advanced Security enabled (SAST, secret scan, Dependabot)
Tooling
• Terraform backend (S3 + DynamoDB) per env | Datadog account
• Amazon Inspector + ECR scanning | tfsec + Checkov
🚀 POC / SHOW & TELL — Tomcat on ECS Fargate
Objective: Prove 'Deployment is a GitHub event – not a human console activity'
What we will demonstrate
1. Developer pushes code (or triggers workflow_dispatch) – no AWS Console
2. GitHub Actions builds Tomcat image from sample-code/tomcat
3. Image pushed to ECR with immutable SHA tag
4. Terraform applies ECS Fargate stack (cluster / service / ALB)
5. ECS service updated; smoke test validates ALB endpoint
6. Deployment summary published: image, SHA, endpoint, workflow run
Success Criteria
✅ No developer AWS console access needed ✅ ECS tasks healthy
✅ ALB returns Tomcat Hello World ✅ Evidence tied to commit SHA
Next hardening: Blue/green deploy · HTTPS · WAF · Private subnets · prod approvals
CONFIDENTIAL | Platform Engineering | App as Code – Phase 1 Baseline v1.0
Prepared for: Newcastle Workshop | June 2026